## Slide 1
IAM Implementation Plan

## Slide 2
Planning | Implementation | Testing and Sandboxing | Journaling | Deployment
5 Weeks | 5 Weeks | 3 Weeks | 3 Weeks | 
Scope | Designed IAM setup | IAM functionality testing | Creation of playbooks/runbooks | Monitoring
Preproduction | Integration with current systems | Vulnerability and pen testing | Training sessions for technical staff and users | Maintenance
Milestone: Completion of Preproduction | Governance and policies | Testing feedback | Final documentation and feedback | Logs and audits
 | Milestone: Completion of integration of IAM | Milestone: Completion of Testing | Milestone: Completion of staff training | Milestone: System maintenance
16 Weeks
Timeline

## Slide 3
Planning | Scope | Preproduction | 5 weeks
Scope
This involves clearly outlining the boundaries and objectives of the IAM integration project. It includes determining which systems, applications, and resources will be included in the IAM solution.
Understanding the stakeholders involved in the project is essential for defining scope. This includes IT administrators, security teams, application owners, and end-users who will be affected by the IAM integration.
Determining the resources required for the integration project, including budget, personnel, and time, falls within the scope definition.
Preproduction
Environment Setup: Before implementing the IAM solution in a production environment, a preproduction environment is set up. This environment mirrors the production environment but allows for testing and validation without impacting live systems.
During preproduction, configurations for user access, roles, permissions, and policies are validated to ensure they align with the defined scope and requirements.

## Slide 4
Implementation | IAM setup | Integration with current systems | Governance and policies | 5 weeks
IAM setup
The IAM solution must align with the integration requirements and provide the necessary features and functionalities. Consider factors such as scalability, compatibility with existing systems
Integration with current systems
Determine which systems and applications need to be integrated with the IAM solution, the level of access control required, and any specific authentication mechanisms needed.
Involve responsibilities of stakeholders, timelines, and milestones. Identify any potential challenges or risks that may arise during the integration process and plan for mitigation strategies.
Governance and policies
Keep up to date with current governance standards and update policies

## Slide 5
Testing | IAM functionality testing | Vulnerability and pen testing | Testing feedback | 3 Weeks
IAM Functionality Testing:
IAM functionality testing aims to verify that the IAM solution performs its intended functions accurately and efficiently.
Testing access control policies, Testing user authentication mechanisms, testing user provisioning/deprovisioning, testing single sign-on (SSO) functionality
Vulnerability Testing:
Vulnerability testing aims to identify and mitigate security vulnerabilities in the IAM solution that could be exploited by attackers.
Simulate real-world attacks to identify potential security weaknesses in the IAM infrastructure, such as misconfigurations, weak authentication mechanisms, or unauthorized access paths.
Feedback:
Feedback gathering involves soliciting input from stakeholders, including IT administrators, end-users, and security professionals, to assess the usability, functionality, and security of the IAM solution.

## Slide 6
Journaling | Playbook, Runbook Creation | Training sessions | Documentation | 3 Weeks
Runbook/Playbook Creation:
Runbooks or playbooks are comprehensive documents that provide step-by-step instructions for performing specific tasks, procedures, or troubleshooting actions related to the IAM solution.
Detailing procedures for recovering from IAM system failures, data breaches, or other security incidents ensures preparedness for worst-case scenarios.
Training Sessions:
Training sessions aim to educate IT staff, administrators, and end-users on how to effectively use, administer, and secure the IAM solution.
Providing hands-on training sessions to IT staff and administrators on configuring, managing, and troubleshooting the IAM infrastructure.
Conducting training sessions or workshops for end-users to familiarize them with the IAM solution's features, access request processes, password management, and security best practices.
Documentation:
Documentation provides comprehensive reference materials, guidelines, and resources for configuring, deploying, and maintaining the IAM solution.

## Slide 7
Deployment | Monitoring | Maintenance | Logs and Auditing
Monitoring:
Monitoring involves continuously observing the IAM infrastructure's performance, availability, and security posture to detect anomalies, errors, or security incidents in real-time.
Implementing proactive measures to identify and address performance bottlenecks, capacity limitations, or security vulnerabilities before they impact system availability or integrity.
Maintenance
Maintenance involves performing routine tasks and updates to keep the IAM infrastructure operating smoothly, securely, and in compliance with organizational policies and regulatory requirements.
Applying security patches, software updates, and firmware upgrades to address known vulnerabilities and improve system stability and performance.
Regularly reviewing and updating configuration settings, access controls, and authentication mechanisms
Logs/Auditing:
Logs and auditing provide a detailed record of user activities, system events, and access-related transactions within the IAM infrastructure, facilitating compliance, forensics, and incident response.